## Slide 1: Action Taken Report (ATR) of the First Extension Education Council Meeting
Dr. A. K. Thakur
Director Extension Education (DEE)
Bihar Animal Sciences University, Patna

## Slide 2: Agenda - 1
Agenda details | Decision/Observation | Action taken
Overviews of extension activities and proposal for adopting the villages as “Poultry Gram” and “Dairy Gram” etc. | Brief Presentation about ongoing extension programme and it was decided to adopt the villages under DEE, BASU, Patna. | B.V.C., Patna adopted two villages as ‘Goat Gram’ and ‘Poultry Gram’, respectively. The village namely ‘Pratappur’ adopted by SGIDT, Patna as ‘Dairy Gram’. The COF, Kishanganj adopted ‘Khanabari’ and ‘Manizor’ villages. In all, 11 villages have been adopted by KVK, Jamui.

## Slide 3: Agenda - 2
Agenda details | Decision/Observation | Action taken
Proposed organizational set-up of DEE, BASU, Patna. | It was decided that DEE would consist of following wings Communication Centre Training wing Publication wing Exhibition wing Field Extension wing including KVK. | To be established in new building.

## Slide 4: Agenda - 3
Agenda details | Decision/Observation | Action taken
Skill Development Programmes to be undertaken in collaboration with Agricultural Skill Council of India (ASCI). | It was decided to undertake Skill Development Programmes in collaboration with ASCI | MOU signed with ASCI, Training of Master Trainers for 10 job roles completed.

## Slide 5: Agenda - 4
Agenda details | Decision/Observation | Action taken
Proposed training centres under BSDM, Govt. of Bihar, Patna. | It was decided to establish training centres at BASU, Patna in collaboration with BSDM, Patna. | Skill Development Centres have been set-up at BVC and SGIDT, Patna in collaboration with BSDM, Patna.

## Slide 6: Agenda - 5
Agenda details | Decision/Observation | Action taken
Veterinary & Animal Sciences Training Centres to be set-up. | It was decided to establish these centres at Research stations transferred to our University. | A proposal for establishing Pashu Vigyan Kendra (PVK) including proposed Training Centre is under consideration of Govt. of Bihar.

## Slide 7: Agenda - 6
Agenda details | Decision/Observation | Action taken
i'kqikyu lwpuk ,oa lsok dsanz (ATIC) to be established. | It was decided to establish ATIC at University Campus. | To be established in new building.

## Slide 8: Agenda - 7
Agenda details | Decision/Observation | Action taken
Organizing ANIFEST/Kisan Mela, Animal Health Camp/Pet Animal Show. | It was decided to organize Animal Health Camp, Pet Animal Show, ANIFEST/Kisan Mela. | Pet Animal Show (Dog Show) and Animal Health Camps have been organized. Kisan Mela to be organized once in a year.

## Slide 9: Agenda - 8
Agenda details | Decision/Observation | Action taken
Proposal for Constituting Extension Committee at college level. | It was decided to Constitute Extension Committee at college level for planning and executing extension activities. | Extension Committee Constituted at college level. Dr. Pankaj Kumar, Nodal Officer, BVC, Patna. Dr. Rakesh Kumar, Nodal Officer, at SGIDT, Patna. Mr. Narendra Kumar, Nodal Officer at COF, Kishanganj.

## Slide 10: Agenda - 9
Agenda details | Decision/Observation | Action taken
Steps to be taken for collaboration with line departments and other agencies. | It was decided to collaborate with line departments and other agencies. | Collaboration and linkages developed with line departments eg. Dept. of Animal & Fisheries Resources, Directorate of Dairy Development, BAMETI, ATMA, BSDM, COMFED, IED, Patna, BAU, Sabour, RPCAU, Pusa, and other organizations eg. ASCI, ICAR-RCER, NRC on Litchi, Reliance Foundation, and VPMU, Patna etc.